## Slide 1: BUILDER TRAINING SERIES
Residential Cost Estimating 101
Notes: Welcome
Welcome to this course on Residential Cost Estimating 101
Presented by Simpson Strong-Tie

## Slide 2: Credit Information
Professional Development Hours
Simpson Strong-Tie® offers Professional Development Hours for completing this course. No other continuing education or accredited credits are available for this course.
This course offers .5 PDH (1/2 hour of PDH credit)
Notes: Credit Information – Professional Development Hours
Simpson Strong-Tie offers Professional Development Hours for completing this course. No other continuing education or accredited credits are available for this course.

## Slide 3: Course Requirements
Pass the Class to Earn Personal Development Hours
EXERCISES
Complete the Knowledge Checks in the course
PASS ASSESSMENT
Pass the Final Assessment at the end of the course
READ & LISTEN
Read and listen to all course material in sequence
Notes: Course Requirements
To pass the class and earn Professional Development Hours, read and listen to all course material in sequence, complete the Knowledge Checks in the course, and pass the final assessment at the end of the course.

## Slide 4: About this Course
Intro for Purchasing Agents, Contractors and Project Superintendents to the basic principles of developing residential construction estimates.
Learning Objectives
Explain the basic concepts in creating residential construction estimates.
Discuss the process to develop a basic estimating project.
Identify the main categories used in the process.
Show commonly used cost centers to be included in a residential construction estimating project.
Notes: Course Description and Learning Objectives
This course introduces Purchasing Agents, Contractors and Project Superintendents to the basic principles used in developing residential construction estimates. The course discusses basic mathematic estimating formulas, cost types used in residential projects, basic parts of project estimating, and tools available for construction estimating.
When you have completed this course, you should be able to:
Explain the basic concepts used in creating residential construction estimates
Discuss the process used to develop a basic estimating project
Identify the main construction categories used in the estimating process
Recite the most commonly used cost centers that would be included in developing a typical residential construction estimating project

## Slide 5: Course Agenda
LESSON 1 Construction Estimating Basics
LESSON 2 Basic Mathematic Formulas Used for Estimating
LESSON 3 Basic Parts of a Project Estimate
Notes: Course Agenda
The topics covered in this course include the following:
Lesson 1
Construction Estimating Basics
Lesson 2
Basic Mathematic Formulas Used for Estimating
Lesson 3
Basic Parts of a Project Estimate

## Slide 6
Residential Cost Estimating 101
LESSON 1
Construction Estimating Basics
Notes: LESSON 1: Construction Estimating Basics
This lesson introduces the basic components of an estimate, the bidding process, and the characteristics of a construction estimator.

## Slide 7: Construction Estimating
Construction estimates include:
  - cost of materials - man-hour rates - equipment performance - overhead costs - profit margin
Forecasting cost and profits
Estimating is a forecast of costs and profits entailed in building the project.
Notes: Construction Estimating
Forecasting cost and profits
Estimating is a forecast or prediction of the costs and profits entailed in building the project
Construction estimating is the process used to estimate future construction costs for a specific project. Construction estimates combine the cost of materials with historical man-hour and equipment performances to arrive at a material, labor, and equipment cost. Then, overhead costs and a margin for profit are included to create a total cost. To remove most of the uncertainty inherent in an estimate requires careful and detailed project cost analysis, accurate estimation of variable costs, and an accurate time frame.
(Student Handout Material)

## Slide 8: Parts of the Estimate
Builder’s Total Cost
Direct Costs
Material, Labor, Burden,
Equipment, Subcontractor
Indirect Costs
Overhead, Office, Administration
Builder’s Profit
Profit, Escalation, Markup
Total Project Cost
Total Project Cost
Costs and profit
Notes: Parts of the Estimate
Costs and profit
This chart illustrates the primary elements contained in a construction total project cost estimate. Estimating is calculating the Total Project Cost, which is the Builder’s Total Cost plus the Builder’s Profit. Review how the different pieces fit together and the following slides will discuss more detail about the individual parts of the estimate.
Estimating = Total Project Cost
Total Project Cost = Builder’s Total Cost + Builder’s Profit
Builder’s Total Cost = Direct Costs + Indirect Costs
(Student Handout Material)

## Slide 9: Builder’s Total Cost
Builder’s Total Cost
Builder’s Total Cost
Total Project Cost
Direct Costs
Material, Labor, Burden,
Equipment, Subcontractor
Indirect Costs
Overhead, Office, Administration
Builder’s Profit
Profit, Escalation, Markup
Total Project Cost
Notes: Builder’s Total Cost
Cost Types Used In Estimates
Calculating the Builder’s Total Cost requires a detailed analysis of the project to determine the Direct and Indirect Costs of the project. The cost types used in residential construction project estimates include: Direct Costs and Indirect Costs. The following slides discuss these cost types in more detail.

## Slide 10: Direct Costs
Direct Costs
Material, Labor, Burden, Equipment, Subcontract Costs
Total Project Cost
Builder’s Total Cost
Indirect Costs
Overhead, Office, Administration
Builder’s Profit
Profit, Escalation, Markup
Total Project Cost
Direct Costs
Material, Labor, Burden,
Equipment, Subcontractor
Notes: Direct Costs
Overview
Direct costs include the cost of materials, labor, burden, equipment, and subcontractors. The following slides review these costs in more detail.

## Slide 11: Direct Costs
MATERIALS
Material costs (raw costs) include Unit Prices for construction goods plus the material Sales Tax.
Lumber, Connectors, Fasteners
Windows
Concrete and Masonry
Doors, Cabinets, and Railings
Electrical Wiring and Fixtures
Plumbing Pipe and Fixtures
HVAC
LABOR
Labor Prices uses Historical Production Rates and are measured in Unit Man-Hours plus labor burden costs and contingencies.
F.I.C.A. (Social Security)
F.U.T.A. (Unemployment tax)
Liability Insurance
Workers Compensation
Payroll Taxes
Component Cost Items
Notes: Direct Costs
Component Cost Items
Material costs, also referred to as raw costs, include Unit Prices for construction goods used during the construction process, plus the material Sales Tax. These costs include the following items:
Lumber, Connectors, Fasteners
Windows
Concrete and Masonry
Doors, Cabinets, and Railings
Electrical Wiring and Fixtures
Plumbing Pipe and Fixtures
HVAC
Labor Prices uses Historical Production Rates and are measured in Unit Man-Hours plus labor burden costs and contingencies including
F.I.C.A. (Social Security)
F.U.T.A. (unemployment taxes)
Liability Insurance
Workers Compensation
Payroll Taxes
(Student Handout Material)

## Slide 12: Direct Costs
BURDEN
Burden costs are additional cost factors affecting man-hour production rates. You may calculate these costs as a percentage of the base labor cost, such as 30%, or as a combined total hourly cost increase, such as an increase of $1.50 per hour for installers.
Skilled Craftsmen Costs
Proper Supervision Costs
Adequate Supply of Labor Costs
Weather Conditions and Seasonal Construction Costs
Coordination With Other Trades Costs
Condition of Work Area Duration of Project Costs
Work Ethics Costs
EQUIPMENT
Equipment Costs are based on equipment production rates and unit pricing.
Owned equipment includes
Initial Costs
Depreciation
Operation
Maintenance Costs
Rental equipment includes
Rental Costs
Operation Costs
Transportation Costs
Set-Up Costs
SUBCONTRACTOR
Subcontracting Costs include individuals or teams of subcontract segments for the project. Different methods can be used.
An in-place unit pricing is where the total building cost is estimated by adding the unit costs for the various building components.
Lump sum costs summates all costs into one inclusive cost.
Cost or percentage for administering and managing the project.
Component Cost Items
Notes: Direct Costs
Component Cost Items
Burden costs are additional cost factors affecting man-hour production rates. The estimator may calculate these costs as a percentage of the base labor cost, such as 30%, or as a combined total hourly cost increase, such as an increase of $1.50 per hour for installers. These additional factors include the following items.
Skilled Craftsmen Costs
Proper Supervision Costs
Adequate Supply of Labor Costs
Weather Conditions and Seasonal Construction Costs
Coordination With Other Trades Costs
Condition of Work Area Duration of Project Costs
Work Ethics Costs
Equipment Costs are based on equipment production rates and unit pricing. However, other common factors affect equipment costs depending on whether the equipment is owned or rented.
Owned equipment includes
Initial Costs
Depreciation
Operation
Maintenance Costs
Rental equipment includes
Rental Costs
Operation Costs
Transportation Costs
Set-Up Costs
Subcontracting Costs include individuals or teams of subcontract segments for the project. Several different methods can be used to determine the subcontract costs.
An in-place unit pricing is a cost-estimating method in which the total building cost is estimated by adding the unit costs for the various building components
Lump sum costs, which is a method that summates all costs into one inclusive cost
Cost or percentage for administering and managing the project
(Student Handout Material)

## Slide 13: Indirect Costs
Indirect Costs
Overhead, Office, Administration
Indirect or overhead costs are not specific to any particular job, but are the costs required to maintain your business activities.
Total Project Cost
Builder’s Total Cost
Direct Costs
Material, Labor, Burden,
Equipment, Subcontractor
Builder’s Profit
Profit, Escalation, Markup
Total Project Cost
Indirect Costs
Overhead, Office, Administration
Notes: Indirect Costs
Overview
Indirect costs, sometimes referred to as overhead expenses, are those that are not specific to any particular job, but are the costs required to maintain the business activities. These costs reflect the depth of the organization, where a small builder may have few indirect costs. The following slide reviews these costs in more detail.

## Slide 14: Indirect Costs
Home office
General and Administrative Costs
Vehicle Expenses
Warehouse and Temporary Facilities
Interest on Borrowed Money
Administration
Personnel
Security Costs
Component Cost Items
Notes: Indirect Costs
Component Cost Items
Indirect costs are costs not directly related to the direct costs. These costs are also referred to as contingency costs or overhead costs and may include the following items.
Home office
General and Administrative costs
Vehicle Expenses
Warehouse and Temporary Facilities
Interest on Borrowed Money
Administration
Personnel
Security Costs
(Student Handout Material)

## Slide 15: Builder’s Profit
Builder’s Profit
Profit, Escalation, Markup
Profit
Escalation Percentage
Markup
Total Project Cost
Builder’s Total Cost
Direct Costs
Material, Labor, Burden,
Equipment, Subcontractor
Indirect Costs
Overhead, Office, Administration
Total Project Cost
Builder’s Profit
Profit, Escalation, Markup
Notes: Builder’s Profet
Profit Calculation Options
Profit is calculated as a percentage of the subtotal cost, for example: 15%. This percentage should be sufficient to cover unforeseen costs and provide the builder with a margin for profit.
Escalation Percentage: If the job is excessive in the projected length of time to complete the project, it may be necessary to add an escalation percentage. Generally, any project over six months in length, the builder adds 1% per month to total costs of the project.
Markup is the amount a business charges above their direct costs to cover both the overhead and the profit for the entire job.

## Slide 16: Bidding Types
The builder prepares a bid proposal- a written proposal quoting the cost of the project.
  Lump Sum
  Cost Plus
  Fixed Fee
A notice to proceed indicates the client has accepted the bid.
Lump Sum
This bid submits the total cost of the project, but does not include item unit price breakdowns. This is the most competitive and most common type of bid proposal where several companies bid on the same project. Usually the lowest bid is awarded the project, however client may consider other factors in the decision to hire a builder.
Cost Plus
This is a negotiated bid proposal between the builder and the client based on the cost of construction plus a percentage for profit and markup.
Fixed Fee
This is a negotiated fixed bid proposal between the builder and the client that cannot change unless the scope of the project changes.
$
$+%
$
Notes: Bidding Types
Presentation Methods
After all of the costs have been determined, the builder prepares a bid proposal. A bid is a written proposal from the builder to the prospective client quoting the cost of the project. There are three types of bid proposals for construction projects.
Lump Sum
This bid submits the total cost of the project, but does not include item unit price breakdowns. This is the most competitive and most common type of bid proposal where several companies bid on the same project. Usually the lowest bid is awarded the project, however client may consider other factors in the decision to hire a builder.
Cost Plus
This is a negotiated bid proposal between the builder and the client based on the cost of construction plus a percentage for profit and markup.
Fixed Fee
This is a negotiated fixed bid proposal between the builder and the client that cannot change unless the scope of the project changes.
If the client accepts the bid, the builder awarded the project is usually sent a notice to proceed or begin the construction phase.
(Student Handout Material)

## Slide 17: Analysis of CSI MasterFormat
The Construction Specifications Institute (CSI) of the United States and Construction Specifications Canada (CSC) have developed a standard for construction contract documents called MasterFormat.
MasterFormat contains 50 main divisions, eg concrete, masonry, metals, finishes, electrical, etc. (as of 2004 edition).
When teams use the standard as a reference in their documents, it increases the communication between project groups.
Construction Classification Standards
Notes: Analysis of CSI MasterFormat
Construction Classification Standards
The Construction Specifications Institute (CSI) of the United States and its Canadian counterpart, Construction Specifications Canada (CSC) have developed a standard for organizing specifications and other written information called MasterFormat. The standard is the most widely used format for how trade associations and manufacturers catalog and file technical literature, and how companies format specifications for construction contract documents, project manuals, drawings, and product literature.
The standard is updated annually and as of the 2004 edition, MasterFormat contains 50 main divisions that consist of items such as concrete, masonry, metals, finishes, and electrical. Each division then contains several subdivision sections to allow for a greater degree of detail. When teams use the standard as a reference in their documents, it increases the communication between project groups.

## Slide 18: Estimator Characteristics
Estimating is critical in making a construction project profitable.
The estimator must ensure the development of proper price-cost-profit foundations.
Strong understanding of the construction process.
Field experience in construction.
In-depth knowledge of construction materials.
Aware of the industry resources available to assist in compiling raw data.
Mathematical ability.
Logical process.
Effective communicator.
Notes: Estimator Characteristics
Industry Requirements
Estimating is one of the most critical functions in making a construction project profitable. By forecasting an accurate estimate of all cost and profit requirements, each component of the construction process proceeds with a set of measureable standards under which to perform. As a result, the estimator must contain certain characteristics and abilities to ensure the development of proper price-cost-profit foundations. This is a list of general characteristics of the modern estimator, but will continue to change as advancements in construction technology continue to take place.

## Slide 19: Check Your Knowledge
The total project cost estimate consists of which of the following items?
Direct costs plus indirect costs
Builder’s total costs and builder’s profit
All direct costs
Materials, labor, and subcontractor costs
Notes: Check Your Knowledge

## Slide 20
Basic Mathematic Formulas Used for Estimating
Residential Cost Estimating 101
LESSON 2
Notes: LESSON 2: Basic Mathematic Formulas Used for Estimating
This lesson introduces the most common types of mathematic formulas used to create a construction estimate.

## Slide 21: Mastering Basic Mathematics
Four Basic Formulas
Length or Linear
Area
Volume
Count
Notes: Mastering Basic Mathematics
Four Basic Formulas
Most construction estimating projects require the use of basic mathematic formulas. While many different formulas and calculations may be required when estimating projects that are more diverse, mastering these four basic formulas and calculations will improve your skills in construction estimating.
The following slides review each of these formulas and calculations in greater detail.
Length or Linear
Count
Area
Volume
(Student Handout Material)

## Slide 22: Length or Linear Measurements
Length determines the end-to-end distance of any item related to the project.
Common units of length in estimating residential construction costs are:
Inch (in.)
Foot / Linear Feet (L.F.)
Yard(s) (yds.)
End-to-End Distance
7 in.
11.5 in.
Total Length Calculation
Add All Measured Sides
11.5 in. + 7 in. = 18.5 in
Notes: Length or Linear Measurements
End-to-end Distance
Length is a simple formula used to determine the end-to-end distance of any item related to a construction or remodeling project. The common units of length in estimating residential construction costs are:
Inch (in.)
Foot / Linear Feet (L.F.)
Yard(s) (yds.)

## Slide 23: Count Measurements
Counts are addition formulas. Items are added up to determine the total number.
Addition Formula
Total Count Calculation
Add Each Item
1 + 1 + 1 + 1 = 4
Notes: Count Measurements
Addition Formula
Some figures in estimates require calculation by counting. Counts are addition formulas and consist of adding items or groups of items one by one to determine the total number.

## Slide 24: Area Measurements
Area calculations are used to determine the quantitative measure of a plane, by multiplying length x width.
Common units of area in estimating residential construction costs are:
Square inches (sq. in. or S.I. or in2)
Square feet (sq. ft. or S.F. or ft2)
Square yards (sq. yd. or S.Y. or yd2)
Extent of a Plane
Total Area Calculation
Length x Width
14 in. x 8 in. = 112 in2
8 in.
14 in.
Notes: Area Measurements
Extent of a Plane
Area calculations are used to determine the quantitative measure of a plane. Area calculations are completed by multiplying length x width. The common units of area in estimating residential construction costs are:
Square inches (sq. in. or S.I. or in2)
Square feet (sq. ft. or S.F. or ft2)
Square yards (sq. yd. or S.Y. or yd2)
(Student Handout Material)

## Slide 25: Volume Measurements
Volume calculations determine the overall amount of space that an object occupies - the area that either needs filling or removing as part of the project.
Volume calculations = multiplying length x width x height. Common units of volume in estimating residential construction costs are:
Cubic inches (in3)
Cubic feet (ft3)
Cubic yards (yd3)
Space of an Object
Total Volume Calculation
Length x Width x Height
12 in. x 10 in. x 7 in. = 840 in3
7 in.
12 in.
10 in.
Notes: Volume Measurements
Space of an Object
Volume calculations are used to determine the overall amount of space that an object or substance occupies. In estimates, volumes determine a specific area that either needs filling or removing as part of a construction or remodeling activity. Volume calculations are completed by multiplying length x width x height. The common units of volume in estimating residential construction costs are:
Cubic inches (in3)
Cubic feet (ft3)
Cubic yards (yd3)

## Slide 26: Check Your Knowledge
Which of the following equations is used to calculate square feet for flooring?
Length x width x height
Length x 2.5 feet
Width x 2.5 feet
Length x width of the floor surface
Notes: Check Your Knowledge

## Slide 27
Basic Parts of a Project Estimate
Residential Cost Estimating 101
LESSON 3
Notes: LESSON 3: Basic Parts of a Project Estimate
This lesson discusses the main elements to include in a residential construction project estimate.

## Slide 28: The Estimating Process
Scoping Specifications Costing Estimate Final Bid
The estimating process is a logical project forecasting sequence
with various time and function allocation phases.
While every residential construction project is unique, certain aspects of the estimate will remain the same for most project estimates.
Average Length of Individual Overlapping Phases
Notes: The Estimating Process
The estimating process is a logical project forecasting sequence
with various time and function allocation phases.
While every residential construction project is unique, certain aspects of the estimate will remain the same for most project estimates. The diagram here provides a logical workflow and when used with other supporting documents can help to create a full and complete project estimate. The following pages discuss each section of the diagram.
(Student Handout Material)

## Slide 29: Scoping
The estimator works with the client and design team to understand the scope of the project.
The site purchase price may or may not be part of the estimate. Regardless, analysis and review of the building site is essential.
The estimator must review any area, city, or subdivision codes and restrictions to determine complete preliminary costs.
PHASE
1
Site Purchasing Issues
Street conditions
Terrain
Preservation of trees and landscaping
Accessibility to utilities
After Site Considerations
Obtain a clear deed
Verify future highway department plans
Projected tax rates
Utility costs
Scoping Specifications Costing Estimate Final Bid
Notes: Phase 1 – Scoping
During the first phase of the estimating process, the estimator must work with the client and design team to understand the scope of the project. The purchase price of the site may or may not be part of the estimate. However, analysis and review of the building site is essential, regardless of the case. The estimator must review any area, city, or subdivision codes and restrictions to determine complete preliminary costs.

## Slide 30: Analysis and Specifications
Scoping Specifications Costing Estimate Final Bid
The estimator visualizes the project, considering the impacts from environmental, weather, or other factors.
Initial drawings, schematics, or blueprints may be available.
Logging notes in an estimating checklist is critical as details become available.
PHASE
2
Engineering Fees
Lot survey
Topography
Drainage patterns
Soil conditions
Mean Sea Level elevators
Builder Property Taxes and Fees During Construction
Interest
Property Taxes
Maintenance
Liability insurance
Assessments
Notes: Phase 2 – Analysis and Specifications
During this phase, the estimator must begin to visualize the project with consideration for impacts from environmental, weather, or other key factors. In some cases, there may already be initial drawings, schematics, or blueprints available. Logging notes in an estimating checklist is a critical step as soon as details become available.

## Slide 31: Costing
Costing is the most time-consuming aspect of estimating.
The estimator begins a comprehensive list of construction costs, called a “Takeoff”. Building plans are reviewed, direct and indirect costs are added.
Estimating checklists, software programs, or internal company methods should help to account for costs. However, these do not replace a skilled and experienced estimator.
PHASE
3
Preliminary Costs
Architect or Plan Fee
Site Plan
Building Permits
Utility Connections
Electrical Service
Materials
Labor
Subcontractor Costs
Labor
Equipment
Overhead
Profit
Scoping Specifications Costing Estimate Final Bid
Notes: Phase 3 – Costing
At this point in the estimating process, the estimator begins to create a comprehensive listing of construction costs, often referred to as a Takeoff. This critical process involves reviewing building plans and determining both direct and indirect costs included in the project. Estimating checklists, software programs, or internal company methods should help to account for costs, however, these items do not replace a skilled and experienced estimator.

## Slide 32: Estimate and Schedule
The estimator summarizes the cost estimate in a formal document.
Internal teams review and provide input.
The estimator should provide a project schedule that includes a firm completion date.
PHASE
4
Scoping Specifications Costing Estimate Final Bid
Notes: Phase 4 – Estimate and Schedule
During this phase, the estimator begins to summarize the cost estimate in a formal document. Internal teams review the document and provide input. Although many factors can hinder or delay the construction process, during this phase the estimator should provide a project schedule that includes a firm completion date.

## Slide 33: Final Bid Negotiation
The estimator presents the complete estimation package to the client, architect, and project manager.
The client may obtain multiple bids; final selection may hinge on many different factors.
Once the project is awarded, the estimator assumes the role of project oversight to ensure the project is executed according to the specifications and timeline outlined in the bid documents.
PHASE
5
Scoping Specifications Costing Estimate Final Bid
Notes: Phase 5 – Final Bid Negotiation
During this final phase, the estimator will present the complete estimation package to the client, architect, and project manager. Generally, the client will obtain multiple bids and the final selection of a builder may hinge on many different factors. It is important to note that once the project is awarded, the estimator assumes the role of project oversight to ensure the project is executed according to the specifications and timeline outlined in the bid documents.

## Slide 34: Construction Estimating Software
Buildertrend
Buildertrend is a web-based project management software for home builders and remodelers to provide a better building experience for homebuyers.
CoConstruct
CoConstruct helps builders and remodelers have worry-free control over all the financials of each and every job that integrates completely with QuickBooks.
Stack
Stack is an easy-to-use, cloud-based takeoff and estimating software for construction contractors. Mac & PC compatible. FREE training and support!
Quick Bid
Quick Bid is a construction estimating software for a variety of trades that helps contractors minimize data-entry mistakes and fine-tune labor.
Pipeline LBM
Pipeline LBM software is a versatile, cloud-based material management and estimating system that transforms ANY takeoff quantities into real-world data.
Computer-based construction estimation and project management software has revolutionized the market. Packages provide automatic calculations and produce detailed professional proposals and estimates. These software tools fit a wide range of user requirements and needs.
Notes: Construction Estimating Software
Computer based construction estimating and project management software has revolutionized the market. Packages provide estimators, builders, and contractors with automatic calculations, as well as produce detailed professional proposals and estimates. The market contains software tools that fit a wide range of user requirements and needs.

## Slide 35: Check Your Knowledge
Which phase of the estimating process usually takes the most amount of time?
Phase 1 – Scoping
Phase 2 – Analysis and specifications
Phase 3 – Costing
Phase 4 – Estimate and schedule
Phase 5 – Formal bid
Notes: Check Your Knowledge

## Slide 36: Summary
This training covered developing residential cost estimates.
Lesson 1 Basic estimating concepts. Types of costs with examples Different types of bids CSI MasterFormat Characteristics of construction estimators.
Lesson 2 Basic mathematic formulas used in construction estimating Formula demonstration.
Lesson 3 The estimating process and phases. Cost items and phase processes Introduction to construction estimating software
Notes: This training covered many different topics on developing residential cost estimates.
The first lesson discussed basic estimating concepts. This included the types of costs that comprise the total project cost along with examples of those costs. The lesson also discussed different types of bids, an overview of the CSI MasterFormat, and characteristics of construction estimators.
The second lesson provided basic mathematic formulas used in construction estimating and provided a calculated demonstration of each formula.
The third lesson provided an overview of the estimating process separated into logical phases. The lesson discussed each phase in detail, along with the cost items and processes that should occur during each phase. Also included in the lesson was an introduction to construction estimating software.

## Slide 37
Residential Cost Estimating 101
ASSESSMENT
Final Assessment
There are 10 questions. You must pass with a score of at least 70%.
Notes: Assessment: Final Assessment
There are 10 questions in the final assessment and you must pass with a score of at least 70%.

## Slide 38: Congratulations!
You have completed this course. Use the Exit button to close the training.
SST-198-07_ResidentialCostEstimating101_v001 Copyright © 2020 Simpson Strong-Tie. All rights reserved.
Notes: Congratulations!
You have completed this course. Use the Exit button to close the training.